## Slide 1: Quality Assurance Plan
Izabela Kuziora izk
Taavi Karvanen tak16

## Slide 2: Why it’s important?
Quality must be considered a priority at the outset of a project and must be taken into account at all stages of the lifecycle. It is important to remember that quality cannot be added to a project at the end; the mentality that says
“we'll have a quality product because we will test it comprehensively at the end”
leads to systems being built that are unlikely to be
correct
reliable

## Slide 3: Organisation of Project
Project Manager
Project Leader
->All students in a group wishing to be Project Leader must propose themselves for this role
->In the event of the project group being unable to choose a Project Leader, the Project Manager will designate one of the students in the group to be the Project Leader
Quality Assurance Manager
Deputy Project Leader
Deputy Quality Assurance Manager

## Slide 4: DOCUMENTATION
Final Report. This document should clearly summarise the achievements of the project
Design Specification. This document must describe the way in which the software will be broken into modules for implementation and must outline the overall functionality of each module.
Test Specification. This document will specify each of the tests to be executed according to the test plan.
Test Report. This must detail the results of testing, reporting the extent to which the system meets the Requirements Specification
User interface specification

## Slide 5: MEETINGS AND REVIEWS
weekly meeting between the Project Manager and the entire project team to discuss technical issues and progress
These meetings will be minuted according to the standard for minutes (we will discuss it later on)
informal meetings may take place between the Project Leader and the Project Manager, or between the Project Group without the attendance of the Project Manager
formal ‘review meeting’
To review current progress and to evaluate the quality of the task being reviewed.
Major reviews will be held to consider the final versions of the user interface specification, the design specification, and the test specification.

## Slide 6: SOFTWARE CONFIGURATION MANAGEMENT
All software modules, associated software documentation, internal working documents, and documents ultimately for release to the customer, should be administered under control of a software configuration management system.
This will handle version control automatically and will keep a history of the development of each configuration item such that earlier versions can be recovered.

## Slide 7: TOOLS, TECHNIQUES, AND METHODOLOGIES
All program code must be written in the specified programming language, unless you have written permission from the Client (the group project coordinator).
Systems produced on the project must execute on platforms provided by the Department of Computer Science, AU, unless otherwise specified.
All code to be delivered must adhere to the standards specified in QA document SE.QA.09, Coding Standards.

## Slide 8: General Document Standards
Izabela Kuziora izk
Taavi Karvanen tak16

## Slide 9: MINUTES OF MEETINGS
Minutes of meetings should be in plain text and should be emailed to all project members within 24 hours of the meeting. They must contain the following information at the start:
a project title, which should include the name of the project (e.g., Group Project 09);
the meeting purpose (e.g., Weekly Project Meeting);
a list of the people present at the meeting plus any apologies;
the place and date of the meeting;
a circulation list, which should include all those present plus other persons as appropriate; for weekly project meetings, all project members plus the Project Manager should receive the minutes.
the author of the minutes;
the date the minutes were produced;

## Slide 10: MINUTES OF MEETINGS
the version number of the minutes, increased if they have to be recirculated because of errors.
Following the above information should be the following headings and descriptions:
Matters arising - this section will describe matters arising from previous meetings
New business - this section will describe each significant new piece of business, numbering each item;
AOB - this section will describe items discussed as any other business (AOB), and each significant point will be numbered.
For all sections of the minutes, actions decided upon must be indicated, and on a new line must be the word ACTION: and the email address of people designated to carry out the action.

## Slide 11: BASIC INFORMATION CONTENT AND LAYOUT
All formal project documents (with the exception of the User Interface Presentation) must contain the following information on the front cover:
a title, which should clearly indicate both the project and nature of the particular document (e.g., Group Project 09 - Design Specification);
the author(s) of the document;
the configuration reference for the document
the date the latest version of the document was produced;
the version number of the document. This should be incremented if a new release of the document is made.
the document status (see QA document SE.QA.08 for details of permitted document statuses);
the name and address of the Department, together with a copyright notice.

## Slide 12: BASIC INFORMATION CONTENT AND LAYOUT
Each page within the document must contain the following information:
a page header containing:
the title of the document (abbreviated if the full title is too long);
the version number of the document
the status of the document, in brackets (e.g. Draft or Released);
a page footer containing:
the phrase Aberystwyth University / Computer Science;
a page number in the form: Page x of y where x is the page number and y is the total number of pages; page 1 will be the front cover.

## Slide 13: SECTIONS WHICH MUST BE INCLUDED
Every formal document must contain the following lists and sections:
• CONTENTS - this list should come after the title page and must list the titles of all sections and subsections together with their page numbers;
CONTENTS
INTRODUCTION
Purpose of this Document
Scope
Objectives
SPECIFIC SECTIONS GO HERE
REFERENCES
DOCUMENT CHANGE HISTORY: version, CCF No., date, sections changed from previous versions, changed by

## Slide 14: PRODUCTION AND INCLUSION OF DIAGRAMS
All diagrams, graphs, pictures, etc. must be drawn or generated by computer and stored in electronic form. Where diagrams, graphs, etc. are input to a document, they must be stored and accessed in the configuration directory along with their parent document according to the procedures specified in QA document SE.QA.08.

## Slide 15: Project Management Standards
Izabela Kuziora izk
Taavi Karvanen tak16

## Slide 16: ORGANISATION
Each project will have a member of staff as a Project Manager, and a student from the group as Project Leader.
The quality assurance activities of the project will be overseen by the Quality Assurance Manager (QA Manager) who is responsible for adherence to the QA Plan, for writing QA procedures where appropriate, and for conducting reviews and audits of the project tasks and deliverables.
The Project Leader and the QA Manager roles are the two major supervisory jobs taken by Project Group members. QA Manager is a fairly full-time activity, but the Project Leader should also have time to take on some technical or documentation task.
Various other major activities are carried out by the Project Group, and it is common for one group member to carry out several of these activities.

## Slide 17: MAJOR ACTIVITIES
Project management – monitoring and directing progress on the project
Quality assurance - all activities and functions concerned with the attainment of quality
Spike work - Exploratory coding to select and establish the suitability of specific techniques, libraries, or other technologies for specific aspects of the product and to develop expertise in their use
Designing the system - working from the provided requirements specification to produce a design specification document detailing how the facilities will be implemented.
Writing the code - working from the design specification to produce source code that matches that design.

## Slide 18: MAJOR ACTIVITIES
Testing the system – the specification and execution of tests designed to demonstrate that the system satisfies the requirements of the customer
Producing maintenance information - the development of documents (e.g. a maintenance manual) and tools (e.g. Shell scripts, Makefiles) which will provide instructions or automated facilities regarding how modifications can be made to the software, and how to rebuild it.
Producing the end-of-project report - the development of a report summarising the activities and final state of the project, identifying the activities carried out by each group member and describing their experiences of the project.

## Slide 19: Project planning
Project plan
The Project Leader will produce a bar chart for the duration of the project. This will be done after week 3 of the project, when the project leader will be appointed, and after a good deal of early investigation has been done. It will indicate the main tasks that need to be done in order to produce a working system by the end of integration week.
Deliverables
The list of project tasks for all group projects must include production of the documents listed in the DOCUMENTATION section of the QA Plan as deliverables. The software and associated tools (e.g. shell scripts, makefiles) should also be included as deliverables. Listings of all software items must be delivered as well as the software itself, and the team should make clear how the software can be rebuilt.

## Slide 20: Project Monitoring
Weekly Tutorial Meetings
Progress Reporting (blog)
Reviews
The Project Manager will meet regularly with the group in order to:
  monitor progress, and confirm work for the following week;
  detect potential schedule slippage;
  adjust plans associated with later development phases in the light of current circumstances;
  discuss project management techniques.